## Sheet1
Week | ML API | Web GUI | Comments/Notes | ML API Estimated Diff | Web GUI Estimated Diff | ML API Est Time | Web GUI Est Time
2021-01-04 | Create automated build env | Set-up Web GUI environment |  | Easy if done before | Easy if done before | 1-2 days | 3 days
2021-01-11 | Create/test CD with Azure Pipeline | Building of basic Web GUI no data |  | Easy if done before | Easy if done before | 1 day | 3-4 days
2021-01-18 | Create initial basic ML API code | Add in basic data population/validation |  | Easy if done before | Easy if done before | 2 days | 2-3 days
2021-01-25 | Develop ML API with prediction code | Enhance Web GUI with real data |  | Easy if done before | Easy if done before | 1 week | 1 week
2021-02-01 | Develop API to use config file | Add in GUI for changing settings |  | Need some experience | Need some experience | 1 week | 1 week
2021-02-08 | Build in basic ML API authentication | Add in login/sign out ability to Web GUI |  | Need some experience | Need some experience | 1 week | 1 week
2021-02-15 | Add in logging/alerting | Display of logging in Web GUI |  | Need some experience | Need some experience | 1 week | 1 week
2021-02-22 | User testing and defect resolution of ML API | User testing/defect resolution of GUI | Dev and Test people | Initially need experienced tester | Initially need experienced tester | 1 week | 1 week
2021-03-01 | User testing and defect resolution of ML API | User testing/defect resolution of GUI | Dev and Test people | Initially need experienced tester | Initially need experienced tester | 1 week | 1 week
2021-03-08 | QA release checks and initial documentation | QA release checks and initial documentation | QA Eng/Developer | QA Eng and Developer required | QA Eng and Developer required | 1 week | 1 week
2021-03-15 | Final updates/sign off of ML API | Final updates/sign off of Web GUI |  | Need some experience | Need some experience | 1 week | 1 week
2021-03-22 | Q1 release of ML API & Q1 review | Q1 release of Web GUI (Frontend) & Q1 review | Q1 Release | Need some experience | Need some experience | 1 day release/ rest review | 1 day release/ rest review
| Goals | Goals
| Initial ML API built | Basic GUI frontend
| Logging/Alerting | Supported on Azure
| Use of configuration files | Flask Web framework
Gunicorn web server