## Sheet1
Week | ML API | Web GUI | Comments/Notes | ML API Estimated Diff | Web GUI Estimated Diff | ML API Est Time | Web GUI Est Time
2021-01-04 | Create automated build env | Set-up Web GUI environment |  | Easy if done before | Easy if done before | 1-2 days | 3 days
2021-01-11 | Create/test CD with Azure Pipeline | Building of basic Web GUI no data |  | Easy if done before | Easy if done before | 1 day | 3-4 days
2021-01-18 | Create initial basic ML API code | Add in basic data population/validation |  | Easy if done before | Easy if done before | 2 days | 2-3 days
2021-01-25 | Develop ML API with prediction code | Enhance Web GUI with real data |  | Easy if done before | Easy if done before | 1 week | 1 week
2021-02-01 | Develop API to use config file | Add in GUI for changing settings |  | Need some experience | Need some experience | 1 week | 1 week
2021-02-08 | Build in basic ML API authentication | Add in login/sign out ability to Web GUI |  | Need some experience | Need some experience | 1 week | 1 week
2021-02-15 | Add in logging/alerting | Display of logging in Web GUI |  | Need some experience | Need some experience | 1 week | 1 week
2021-02-22 | User testing and defect resolution of ML API | User testing/defect resolution of GUI | Dev and Test people | Initially need experienced tester | Initially need experienced tester | 1 week | 1 week
2021-03-01 | User testing and defect resolution of ML API | User testing/defect resolution of GUI | Dev and Test people | Initially need experienced tester | Initially need experienced tester | 1 week | 1 week
2021-03-08 | QA release checks and initial documentation | QA release checks and initial documentation | QA Eng/Developer | QA Engineer required | QA Engineer required | 1 week | 1 week
2021-03-15 | Final updates/sign off of ML API | Final updates/sign off of Web GUI |  | Need some experience | Need some experience | 1 week | 1 week
2021-03-22 | Q1 release of ML API & Q1 review | Q1 release of Web GUI (Frontend) & Q1 review | Q1 Release | Need some experience | Need some experience | 1 day release/ rest review | 1 day release/ rest review
Q2 Release
2021-03-29 | Sprint planning for Q2 release | Sprint planning for Q2 release | Sprint Planning | Experienced Developer/Scrum Master | Experienced Developer/Scrum Master | 1 week | 1 week
2021-04-05 | Add in additional prediction data | Enhance Web GUI to handle new fields of data |  | Need some experience | Need some experience | 1 week | 1 week
2021-04-12 | Capture of extended data from specific area | Add in search - PostCode/Zipcode | 2 developers | Experienced Developer | Experienced Developer | 1 week | 1 week
2021-04-19 | Capture of extended data from specific area | Add in Map/Statelite capture | 2 developers | Experienced Developer | Experienced Developer | 1 week | 1 week
2021-04-26 | Create iniitial Mobile app | Development of Mobile App frontend | 2 developers | Experienced Developer | Experienced Developer | 1 week | 1 week
2021-05-03 | Create iniitial Mobile app | Development of Mobile App frontend | 2 developers | Experienced Developer | Experienced Developer | 1 week | 1 week
2021-05-10 | Add in location services for specific prediction | Enhance Web GUI for location/Add in Map capture | 2 developers | Experienced Developer | Experienced Developer | 1 week | 1 week
2021-05-17 | Document additional features | Documentation updates for frontend |  | Developer - Easy | Developer - Easy | 1 week | 1 week
2021-05-24 | User testing and defect resolution | User testing/defect resolution of GUI | Dev and Test people | Initially need experienced tester | Initially need experienced tester | 3 days testing/3 days defect | 3 days testing/3 days defect
2021-05-31 | User testing and defect resolution | User testing/defect resolution of GUI | Dev and Test people | Initially need experienced tester | Initially need experienced tester | 3 days testing/3 days defect | 3 days testing/3 days defect
2021-06-07 | QA release checks | QA release checks |  | QA Engineer required | QA Engineer required | 1 week | 1 week
2021-06-14 | Final updates/sign off of ML API | Final updates/sign off of Web GUI |  | Need some experience | Need some experience | 1 week | 1 week
2021-06-21 | Q2 release of ML API & Q2 review | Q2 release of Web GUI (Frontend) & Q2 review | Q2 Release | Need some experience | Need some experience | 1 day release/ rest review | 1 day release/ rest review
Q3 Release
2021-06-28 | Sprint planning for Q3 release | Sprint planning for Q3 release | Sprint Planning | Experienced Developer/Scrum Master | Experienced Developer/Scrum Master | 1 week | 1 week
2021-07-05 | Develop API to take in financial data from sources | Enhance Web GUI/Mobile App to display financial data | 2 developers | Experienced Developer | Experienced Developer | 1 week | 1 week
2021-07-12 | Develop API to take mortgage data from sources | Enhance Web GUI/Mobile App to display mortgage data | 2 developers | Experienced Developer | Experienced Developer | 1 week | 1 week
2021-07-19 | Enhance ML API for comparison of predictions | Add in comparison web page and link to data | 2 developers | Experienced Developer | Experienced Developer | 1 week | 1 week
2021-07-26 | Enhance Mobile App for comparison of predictions | Adapt Mobile App frontend for prediction comparisons | 2 developers | Experienced Developer | Experienced Developer | 1 week | 1 week
2021-08-02 | Create initial documentation/release notes | Create documentation/release notes for frontend |  | need some experience | need some experience | 1 week | 1 week
2021-08-09 | User testing and defect resolution | User testing/defect resolution of GUI | Dev and Test people | Initially need experienced tester | Initially need experienced tester | 3 days testing/3 days defect | 3 days testing/3 days defect
2021-08-16 | User testing and defect resolution | User testing/defect resolution of GUI | Dev and Test people | Initially need experienced tester | Initially need experienced tester | 3 days testing/3 days defect | 3 days testing/3 days defect
2021-08-23 | Finalise documentation of new features for release | Finalise documentation and of Mobile and Web GUI |  | need some experience | need some experience | 1 week | 1 week
2021-08-30 | QA release checks | QA release checks |  | QA Engineer required | QA Engineer required | 1 week | 1 week
2021-09-06 | Final updates/sign off of ML API/Mobile | Final updates/sign off of Mobile App/Web GUI |  | Need some experience | Need some experience | 1 week | 1 week
2021-09-13 | Q3 release of ML API (incl Mobile)/ Q3 review | Q3 release of Mobile App/Web GUI & Q3 review | Q2 Release | Need some experience | Need some experience | 1 day release/ rest review | 1 day release/ rest review
Q4 Release
2021-09-20 | Sprint planning for Q4 release | Sprint planning for Q4 release | Sprint Planning | Experienced Developer/Scrum Master | Experienced Developer/Scrum Master | 1 week | 1 week
2021-09-27 | Build in additional logging/alerting | Continue to adapt Mobile App/Web GUI |  | need some experience | need some experience | 1 week | 1 week
2021-10-04 | Carry out user testing and defect resolution | Carry out user testing and defect resolution | Dev and Test people | Initially need experienced tester | Initially need experienced tester | 3 days testing/3 days defect | 3 days testing/3 days defect
2021-10-11 | Produce updated documentation | Produce additional documentation |  | need some experience | need some experience | 1 week | 1 week
2021-10-18 | Q4 release of initial new ML API | Q4 release of new configurable Web GUI forntend |  | Need some experience | Need some experience | 2 days / 3 days support | 2 days / 3 days support
2021-10-25 | Deploy Q4 release to field | Deploy Q4 release to field | Q4 Release | Need some experience | Need some experience | 2 day release/ 3 day review | 2 day release/ 3 day review
2021-11-01 | Identify new pre-trained ML models from product | Develop Web GUI mock ups | New ideas from Product | Experienced Developer/Product Owner | Experienced Developer/Product Owner | 1 week | 1 week
2021-11-08 | Identify new pre-trained ML models from product | Develop Web GUI mock ups | New ideas from Product | Experienced Developer/Product Owner | Experienced Developer/Product Owner | 1 week | 1 week
2021-11-15 | Develop generic pre-trained ML API model | Develop generic pre-trained ML Web GUI model | 2 developers | Experienced Developer | Experienced Developer | 1 week | 1 week
2021-11-22 | Develop generic pre-trained ML API model | Develop generic pre-trained ML Web GUI model | 2 developers | Experienced Developer | Experienced Developer | 1 week | 1 week
2021-11-29 | Adapt for new specific pre-trained ML model | Adapt Web GUI for new specific pre-trained model | 2 developers | Experienced Developer | Experienced Developer | 1 week | 1 week
2021-12-06 | Initial User Testing and defect resolution | Initial User Testing and defect resolution | Dev and Test people | Initially need experienced tester | Initially need experienced tester | 3 days testing/3 days defect | 3 days testing/3 days defect
2021-12-13 | Review of planned work (Y1) / preview Y2 | Review of planned work (Y1) / preview Y2 | Year review
| Goals | Goals
Q1 | Initial ML API built | Basic GUI frontend
| Logging/Alerting | Supported on Azure
| Use of configuration files | Flask Web framework
Gunicorn web server
Q2 | Extended coverage of prediction | Supported on AWS platform
| Add in additional prediction data | Updates to Web GUI for new prediction data
| First Mobile App (iPhone/Andriod) | First Mobile App (iPhone/Andriod)
| Location services added | Menu options added
Q3 | Enhanced Mobile App backend | Supported on GCP platform
| Add in Financial (mortgages) links | Enhanced Mobile App for frontend
| Add in Estate Agent / Realtor links | Images of houses (linked to external entities)
Q4 | Identify other pre-trained ML APIs | Creation of new Web GUI mock up for extended models
| Adapt for new Product | Iniitial porting of Web code to new models